## Launch Plan
Pre-Launch Timeline/Needs
Phase 1: Sales
- Access | Client provides team with access to necessary tools - AdWords, adCenter, Analytics, WMT, etc.
- Budget | Client provides team with media budget.
- Marketing Plan/Calendar | Client to provide team with a calendar of all upcoming offers, specials, etc.
- Competitive Analysis | Client to provide team with list of traditional competitors. Team provides analysis of traditional and online competition in the paid search space.
- Relationship Notes | Sales provides AM with insights into client.
- Timeline (Service Framework) | Client and team agree upon launch timeline and expectations.
Phase 2: Discovery & Strategy
- Dicovery Document/Questionnaire | Client fills out discovery document with as much background information as possible.
- Dicovery Review Meeting | Team reviews discovery document with client.
- Goals & Expectations | Client and Team agree upon goals and set expectations
- Strategy | Team provides client with account strategy based on client goals, industry trends, best practices and competitive set.
- Project Plan | Team determines activities/strategies by frequency. (Frequency determined internally by hours but hours not shared with client).
- Client Sign Off | Client signs off on goals, timeline, strategy and project plan.
Phase 3: Account Build & Set Up
- AdWords & Bing Ads Account Set Up | Team creates accounts for client in relevant interfaces, links the accounts with Analytics/DART/etc.
- Tracking | Team provides client with tracking and remarketing tags. Client implements tags on pages noted by team.
- Billing | Client/Team to set up billing in all paid search accounts.
- Account Structure, KWs & Ad Examples | Team provides account structure along with keyword and ad copy examples
- Structure & Example Review | Client reviews structure and examples. Client & Team discuss feedback.
- Account Build | Team builds out remaining keywords and ad copy based on client feedback.
- Final Build Review | Client & Team reviews & finalizes build.
- Acquisio Set Up | Team creates Acquisio account for client.
Phase 4: QA & Test
- Account QA | Team to QA AdWords, Bing ads, etc. to ensure perfection. (i.e. bids, budget, spelling, etc.)
- Tracking Test | Team to test tracking to ensure it is working correctly.
- LP Testing | Team to test URLs to ensure all are working properly.
LAUNCH!!!

## Example Project Plan
Champion Nutrition SEO/SEM Project Plan
Q3 | Task | Task description | Owner | Due Date | Status
June | Kick Off Call | Discovery the digital goals of the website and crete a tactical strategic intitiave to meet those goals as best seen from the search engines point of view. | Entire Team | 2012-06-29 | Completed
July | Banner Display Ad Mock Ups | Begin mock ups banners and spotlights - couple comps of each major size - follow up week before sizzle | Forrest | 2012-07-20 | Scheduled
July | Discovery Questionnaire | Lydia to fill out SEM portion of questionnaire | Lydia | 2012-07-06 | In Progress
July | Discovery Questionnaire | Review Discovery Doc feedback from Client create Client Briefing Doc | Dan |  | Begins with Return of Disco Doc
July | Initial Strategy Build | Create Strategy & Goals based off of Discovery Doc | Dan | 2012-07-31 | To Do
July | Initial Strategy Build | Create Account Campaign Structure i. Structure based off of Client Goals, Site Architecture & Products/Service | Dan | 2012-07-31 | To Do
July | Initial Strategy Build | Build Sample Campaign, Sample Ad Copy & Budgets i. Build 1 Brand Campaign & 1 Non Brand Campaign 1. Create thematic, tightly-knit ad groups (Google KW Tool) 2. Write ad copy that is specific to each ad group, using language from the most relevant page. | Dan | 2012-07-31 | To Do
August | Client Review | Review Account Outline, Strategy/Recommendation Doc, Campaigns, Ad copy suggestions, with Client & Get Approval | Dianna/Dan | 2012-08-30 | To Do
August | Final Campaign Builds | Build Final Campaigns, Ads, Keywords
August | Landing Page Recommendations | Recommend Landing Pages for Campaigns and Call to Actions | Dianna | 2012-08-15 | To Do
August | Create Accounts with Providers | i. Create Google Account (BFO MCC) ii. Create adCenter Account iii. Create Campaign Management Software Account | Dan | TBD | To Do
August | Upload | Upload campaigns into AdWords & AdCenter | Dan | TBD | To Do
August | Billing | Budgets & Billing Setup in Campaign Dashboards | Dan | TBD | To Do
August | Billing | Create Budget/Billing Documents | Dan | TBD | To Do
August | Tracking | Create AdWords Conversion Tracking Tags, Analytics Tracking Tags & Remarketing Tags | Dan | TBD | To Do
August | Tracking | Implement tracking tags | Lydia | TBD | To Do
September | Quality Assurance/Testing | QA/Test - Review each ad for functionality, spelling, URL, tracking | Dan | TBD | To Do
October | Launch/Traffic | SEM Campaign LIVE LAUNCH | Dan | TBD | To Do
October | Launch | Daily check-in and optimization/validations for 1-2 weeks i. Day 1 1. Are we live? 2. Quality Score assessment 3. Ad Preview tool | Dan | TBD | To Do
October | Launch | ii. Day 2 1. Bid strategy/average position assessment 2. Reposition ads to position and goal 3. Set up launch bid strategies | Dan | TBD | To Do
TBD | Ongoing Campaign Maintenance |  | Dan | TBD | To Do
Ongoing | Reporting | Monthly Reporting | Dan | TBD | To Do
Ongoing | Bid/Budget Management | Manage bids/budgets to ensure KPI's in line w/ goals.
Ongoing | Search Query Analysis | Opportunities for negative/additional keywords | Dan | TBD | To Do
Ongoing | Landing Page/Ad Copy Testing | Test LPs & Ad Copy | Dan | TBD | To Do
Ongoing | Quarterly Review | Review Performance Quarterly - areas of opportunity, expansion, etc. | Dan | TBD | To Do

## Sheet3
Hurricane Golf SEM Project Plan |  |  | 2013-02-25 | [29 empty] | 2013-03-30 | [30 empty] | 2013-04-16
| Start Dates | Due Dates | 2012-07-02 | [6 empty] | 2013-02-08 | [6 empty] | 2013-02-15 | [6 empty] | 2013-02-22 | [6 empty] | 2013-03-01 | [6 empty] | 2013-03-08 | [6 empty] | 2013-03-15 | [6 empty] | 2013-03-22 | [6 empty] | 2013-03-29 | [6 empty] | 2013-04-05 | [6 empty] | 2013-04-12 | [6 empty] | 2013-04-19 | [6 empty] | 2013-04-26
 | time axis 2013-02-01 to 2013-05-02
Phase 1 - Pre Launch | 2013-02-01 | 2013-03-01
Create Updated Ad Copy for Pre-Launch | 2013-02-08 | 2013-02-15
Submit Ad Copy for Approval | 2013-02-09 | 2013-02-16
Google Analytics Account Access | 2013-02-10 | 2013-02-10
Paid Search Account Access for Adwords & Bing | 2013-02-10 | 2013-02-22
Activate Billing in Adwords & Bing | 2013-02-10 | 2013-03-01
Setup Google Adwords Tracking Tags | 2013-02-22 | 2013-02-25
Setup BingAds Tracking Tags | 2013-02-22 | 2013-02-25
Capture Historical Campaign Performance | 2013-02-22 | 2013-02-28
Update Keyword Level Tracking | 2013-02-22 | 2013-02-28
Begin Pre-Launch Campaign Audit | 2013-02-27 | 2013-02-28
Campaign Pre-Launch QA | 2013-02-27 | 2013-03-01
Setup Google Analtyics Auto Tagging & UTMs | 2013-02-27 | 2013-03-01
Prepare Campaign for Launch | 2013-02-28 | 2013-02-28
Link Paid Search Accounts to Acquisio | 2013-03-01 | 2013-03-01
Phase 2: Launch | 2013-03-01 | 2013-03-01
Launch Google Adwords | 2013-03-01 | 2013-03-01
Launch Bing Ads | 2013-03-01 | 2013-03-01
QA Live Ads & Keywords | 2013-03-01 | 2013-03-01
Phase 2: Post Launch Activities (TBD) | 2013-03-01 | 2013-03-01
Campaign Restructures | 2013-03-08 | 2013-03-15
Ad Copy Revisions | 2013-03-09 | 2013-03-16