## Meeting Notes
Champion Nutrition Meeting Notes
Date | Message | For Who? | Action Needed?
2012-06-29 | Kick Off Meeting - Attended - Forrest, Lydia, Steve K. & Dianna
Design Comps are done and approved. Loaded the wireframes into this spreadsheet.
Forrest to send over approved website copy. Done - Find Here.
| Keyword research scheduled and loaded into project plan. | Dianna | Scheduled
Forrest and Dianna to schedule brand walk- thru. Sched Monday 7/2 1pm.
| Lydia to set up ChicagoGATeam@gmail.com into the Champion Nutrition Google Analytics - Email sent | Lydia | Set Up
Championnutrition.com will become a splash page - seperates out into bodybuilders = championnutrition.com and ambition.championnutrition.com becomes the new champion brand.
| Forrest requested we maintain the SEO and SEM project plan all in one document. | Dianna | Modified
Forrest creating mocks ups of display ads for banners and spotlights
2012 - all ecomm and call center /2013 products in store "Whole Foods" by July
Oct through December soft launch - January - Heavy Marketing for resolution season
| Estimated date for staging dev site is July 31st. | Forrest

## SEO Project Plan
Champion Nutrition SEO/SEM Project Plan
Q3 | Task | Task description | Owner | Due Date | Status
June | Kick Off Call | Discovery the digital goals of the website and crete a tactical strategic intitiave to meet those goals as best seen from the search engines point of view. | Entire Team | 2012-06-29 | Scheduled
June | Content | Content Copy Finalized and Sent Over to Begin Keyword Research | Forrest | 2012-06-29 | Completed
July | Keyword Research | Analyze your website and research keyword themes that are relevant, have high search volume, and offer a competitive advantage. We recommend the keywords that provide the most value, are the most relevant, and have the most potential for website lead generation | Dianna | 2012-07-15 | Scheduled
July | Dev Website Access | Kevin to provide dev access for BFO to look under the hood at the website foundation structure in order to create pre-launch best practices recommendations for SEO. | Kevin | 2012-07-15 | To Do
July | SEO Technical Audit | Staging Site Review: Audit of pre-launch recommendations. | Dan Reno | Dependent on Dev Access Time | Scheduled

## SEO Pre-Launch Tasks
Champion Nutrition Pre-Launch SEO Tasks
Phase | Pre-Launch Task Description | Who Completes? | Due Date | Status | Notes
Pre-Launch | URLs - Search engine friendly URLs in all navigation structure including any left or right hand linking to other internal product pages. | Dev
Pre-Launch | 301 Redirects - website must permanently redirect website domains and URLs to new equivalent URLs with a 301 redirect script or .htaccess file. | Search |  |  | Might not applicable unless we are migrating any URLs from a previous website
Pre-Launch | Custom 404 Page - In case any links are found broken, we need to have an established 404 Error page with navigation category URLs page for usability and retention. | Dev
Pre-Launch | Page Titles - Unique Meta titles for each page and product page. Limit to 70 characters with spaces. Lead with most desired keyword phrase to rank on the page and end with company name. | Search
Pre-Launch | Meta Descriptions - Unique Meta descriptions for each page. Search engines score relevancy to Meta data to their content. Lead with most desired keyword phrase for the page. Limit to 160 characters with spaces. | Search
Pre-Launch | Site Map (HTML & XML) - Indexing assistance for search engines. HTML sitemap page consists of main, category and product level links directly into their pages for user retention. Place the HTML link in the footer of the website. XML sitemap is a file used specifically to help the search engines find and index the URLs quickly. | Search
Pre-Launch | Webmaster Tools - Google and BING webmaster tools are control panels for monitoring crawls of the website as well as URL indexation and additional keyword analytics data. | Search
Pre-Launch | Google Analytics - We will provide the most current script for the Google Analytics account to enable many of the new reporting features it now offers. | Search
Pre-Launch | Canonicalization - Page canonicalization helps the search engines determine which version is the unique, original and removes duplicity penalties for numerous version of a page. Especially helpful in eCommerce. | Search |  |  | Try to avoid any "reductive" navigation
Pre-Launch | Robots.txt - File to communicates to bots across the web, which areas to the website are indexable and which are not. A URL to the XML sitemap is also listed here for thoroughness. | Search
Pre-Launch | Mobile script for website to redirect mobile users to mobile version of website | Dev |  |  | Will there be a mobile website version?
Pre-Launch | Alt Text Image Attributes - An image file name and the alt text assigned to it is a trigger to the search engines content for the image. Label the image both with a search engine friendly file name and alt text content. | Dev
Pre-Launch | Image Title attributes - By adding the image title attribute, browsers such as Firefox, Safari and more are able to read the al t text. It will not be limited to only IE users. This also helps software for the vision impaired to read the content of the image and keep the website in handicap accessibility compliace. | Search
Pre-Launch | Link Title Attributes - By adding the link title attribute, browsers such as Firefox, Safari and more are able to read the link text. It will not be limited to only IE users. This also helps software for the vision impaired to read the content of the link and keep the website in handicap accessibility compliace. | Search

## Wireframes
Product Pages --->
| Webpage Wireframes | Products Main | Products Detail | Get Fit A | Get Fit B | Get Fit C
Company Pages --->
ambition.championnutrition.com

## Web Content
Champion Website Content Copy
Sent 27 June 2012
HOME PAGE
Rotating Headlines:
Reach for your fitness goals.
Get as strong as you can envision.
Go as far as your mind can see.
Play as hard as you can imagine.
Your mind says you can do it. Now make it happen. | What’s your ambition? | Original Champion Products
Build on your hard work with a system of healthy nutritional products designed to help your body live up to your mind’s ambition. | Get Fit | Shop our original Champion Nutrition Products designed for bodybuilding, fitness, and wellness online.
Get Stronger
> Explore our products | Go Farther | > Go now
Play Harder
See products, training tips, and inspirational stories that can help you get there faster and healthier.
Get 10% off your first order!
Just sign up for our newsletter for special offers, training tips, and new products alerts.
[Enter email] >
PRODUCTS PAGE
Home > Products
Fit | Explore the Champion system of healthy workout products scientifically formulated to give your body the nutrition it needs to reach your mind’s ambition.
Endurance
Strength | Daily Protein
Sport | Improve results with blended protein designed specifically for your athletic ambition combined with a health boosting nutritional base – all in a great tasting powder you can use to make or add to a shake.
FIT
Energize | Just starting out or getting back on track? Champion Fit gives you the protein and nutrients you need to get fit and stay healthy. More
Sustain
Recharge | ENDURANCE
However you put your miles in – running, cycling, swimming, or a combination of all three – Champion Endurance can help you go farther. More
Focus
Reboot | STRENGTH
Lift harder and recover faster with the right amount of whey protein, creatine, BCAAs, and enzymes that promote protein absorption. More
Get 10% off your first order! | SPORT
Just sign up for our newsletter for special offers, training tips, and new products alerts. | No matter what sport you play from racquetball to basketball, Champion Sport will help you play harder and recover quicker. More
[Enter email] >
Workout Support
Enjoy the FREE benefits of the Champion Ambition program. | Give your body the healthy energy and nutritional support it needs to power through every workout from start to finish.
· Save 10% on all orders
· Create a custom program based on your ambition | ENERGIZE
· Set up convenient auto shipments and never run out | Kick start your workout with an instant infusion of sustained energy packed with vitamins, minerals, and antioxidants. More
· Get priority customer service
> Sign up now! | SUSTAIN
Push your workout further with an innovative combination of ingredients that boost hydration and sustained energy. More
RECHARGE [New name and description TBD]
Speed your workout recovery with nutrition designed to replenish and repair your body so you can do it all over again. More
Mind & Body Boosters
Empower your mind and body with focus enhancing and plateau busting formulas that will help you take it to the next level.
FOCUS
Increase mental energy, alertness, and reaction time with a brain boosting formula designed to help your mind push your body hard towards your goals. More
REBOOT
Bust through any plateau with a reenergizing cleanse that improves athletic performance by removing toxins and preparing your body to absorb nutrition better. More
FIT PRODUCT PAGE
Home > Products > Fit
Fit | Daily Protein | [Product Image]
Endurance | Fit | Increase Fitness • Boost Health • Promote Metabolism
Strength | Get fit and stay healthy.
Sport | > Supplement Facts | Net Weight: 3lbs (1.36 kg)
| > FAQ | Regular Price: $XX.XX
Energize | > Reviews | Sale Price: $XX.XX
Sustain
Recharge | Get fit and stay healthy. | [1] > Add to cart
Champion Fit contains the right amount of blended protein – shown to be more effective than a single source – to support your fitness ambitions. That’s combined with a nourishing mix of natural and scientifically-proven ingredients you won’t find anywhere else.
Focus
Reboot | · Increase fitness with 18 grams of brown rice and essential amino acid packed pea protein with a food based multivitamin mix. | Complete the system
· Boost health and speed recovery with powerful antioxidants derived from a unique combination of berries, vegetables, and herbs.
| · Promote metabolism, optimize protein absorption, and minimize digestive issues with essential enzymes and herbal extracts. | Energize
Get 10% off your first order! |  | Power your workout.
Just sign up for our newsletter for special offers, training tips, and new products alerts. | Champion Fit is gluten free, dairy free, allergen free, and plant-based, and made with only safe and healthy ingredients with no artificial flavors or fillers.
[Enter email] > |  | Sustain
| It’s available in absolutely great tasting chocolate or vanilla. Just add to a healthy shake and drink 30 minutes before and after your workouts to see your best results. | Push your workout further.
Enjoy the FREE benefits of the Champion Ambition program. | With more than 30 years of experience in sports nutrition, we’re ready to help your body reach the fitness goals your mind can envision. | Recharge
· Save 10% on all orders |  | Speed your recovery.
· Create a customized program based on your ambition | Are you ready to get fit?
· Never run out with convenient auto shipments |  | Focus
· Get priority customer service | Get Fit | Empower your mind.
· No obligation – cancel anytime | Don’t go it alone. Find training tips and inspirational stories to help you get fit faster and healthier.
> Sign up now! | > Start now
GET FIT PAGE
Home > Ambitions > Get Fit
Get Fit | Your Ambition | Your Nutritional System
Go Farther | Get Fit | Reach your fitness ambition with a system of healthy and scientifically formulated products.
Get Stronger
Play Harder | ROTATING COPY AT TOP: | Fit
| How much is enough? | Get fit and healthy with our unique Fitness Protein Blend combined with a healthy nutritional base.
Adults need 150 minutes of moderate or 75 minutes of vigorous aerobic activity and strengthening activities on 2 or more days every week according to the Center for Disease Control and Prevention (CDC).
Get 10% off your first order! |  | Energize
Just sign up for our newsletter for special offers, training tips, and new products alerts. | 10 minutes at a time is fine. | Power your workout.
[Enter email] > | Break down the CDC’s recommendation for aerobic activity into 10 minutes chunks to work it into your day more easily. Go for a brisk walk, hike up and down stairs, or do jumping jacks.
Sustain
| How many reps? | Push your workout further.
Enjoy the FREE benefits of the Champion Ambition program. | To get the most out of lifting weights, lift to the point where it’s hard to do another rep without help. Start with 1 set of 8 to 12 reps and work your way up to 2 or 3 sets. If it’s too easy, add more weight.
· Save 10% on all orders |  | Recharge
· Create a customized program based on your ambition |  | Speed your recovery.
· Never run out with convenient auto shipments | It takes time and effort to get fit and healthy no matter what point you’re starting from. You have to see your goal in your mind – whether it’s losing 10 pounds or running your first 5K – and push your body to work hard. Our innovative system of products was designed to build on that hard work by giving your body the nutrition it needs to live up to your mind’s ambition.
· Get priority customer service |  | Focus
· No obligation – cancel anytime | This system takes into account your fitness ambition, body and mind, and workout cycle from preparation to recovery and beyond: | Empower your mind.
> Sign up now!
| · Champion Fit contains a unique Fitness Protein Blend to build lean and healthy muscle combined with nutrients to promote health and metabolism. | Reboot
| · Champion Energize, Sustain, and Recharge provide workout support to help you ramp up, power through, and recover faster. | Revitalize your body.
· Champion Focus improves performance by upping your mental energy and acuity.
· Champion Reboot helps you burst through any plateau with a reenergizing 7-day cleanse.
Along with these products, we’ve put together training tips and inspirational stories from real people who share your ambition to help you achieve your fitness goals.
Training Tips
[Intro in to Article]
> Read more > See all tips
Real Stories
[Intro to Story]
> Read more > Read all stories
GO FARTHER PAGE
Home > Ambitions > Go Farther
Get Fit | Your Ambition | Your Nutritional System
Go Farther | Go Farther | Reach your fitness ambition with a system of healthy and scientifically formulated products.
Get Stronger
Play Harder | ROTATING COPY AT TOP: | Endurance
| Just starting out? | Go farther with our unique Endurance Protein Blend combined with a healthy nutritional base.
With the right training, virtually anybody can experience the healthy high you get during an endurance race whether it’s a 5K run or 30 mile cycle. Look online for shorter distance events in your area and add miles as you get into the groove.
Get 10% off your first order! |  | Energize
Just sign up for our newsletter for special offers, training tips, and new products alerts. | Hydrate, hydrate, hydrate. | Power your workout.
[Enter email] > | Keeping your body hydrated is essential for endurance. But don’t just hydrate during workouts or races – drink at least 8 8-oz glasses of water a day and even more on hard training days. Remember, if you feel thirsty, you’re already dehydrated.
Sustain
| Don’t try anything new on race day. | Push your workout further.
Enjoy the FREE benefits of the Champion Ambition program. | Race day isn’t the time to throw on new sneakers or try a new nutritional supplement to barrel through the wall. Make sure you test everything out during your training so you’ll feel confident and ready to go on the big day.
· Save 10% on all orders |  | Recharge
· Create a customized program based on your ambition |  | Speed your recovery.
· Never run out with convenient auto shipments | It’s hard work to put in mile after mile whether you’re running, swimming, or cycling, but you can see your goal in your mind, so you push your body forward. Our innovative system of products was designed to build on that hard work by giving your body the nutrition it needs to live up to your mind’s ambition.
· Get priority customer service |  | Focus
· No obligation – cancel anytime | This system takes into account your fitness ambition, body and mind, and workout cycle from preparation to recovery and beyond: | Empower your mind.
> Sign up now!
| · Champion Endurance contains a unique Endurance Protein Blend to build muscle without adding bulk combined with nutrients to promote absorption and speed recovery. | Reboot
| · Champion Energize, Sustain, and Recharge provide workout support to help you ramp up, power through, and recover faster. | Revitalize your body.
· Champion Focus improves performance by upping your mental energy and acuity.
· Champion Reboot helps you burst through any plateau with a reenergizing 7-day cleanse.
Along with these products, we’ve put together training tips and inspirational stories from real people who share your ambition to help you achieve your endurance goals.
Training Tips
[Intro in to Article]
> Read more > See all tips
Real Stories
[Intro to Story]
> Read more > Read all stories
Who We Are Page
Home > Company > Who We Are
Who We Are | Who We Are
Our Philosophy | Champion Nutrition has been an innovator in sports nutrition since our founding in 1986. We’re committed to developing effective, safe, healthy, and high quality nutritional products that help you push your body to reach your mind’s athletic ambitions.
News & Events
Contact Us | We have a broad base of industry knowledge that extends through our parent company Nature’s Products Incorporated (NPI). NPI’s manufacturing capabilities and strong infrastructure complement our experience providing athletes and fitness enthusiasts with results-driven products that build on their hard work.
We’re deeply committed to quality, which is demonstrated by our nearly 30 year history of creating and distributing safe and healthy products. Our in-house 135,000 square foot GMP-certified manufacturing facility in Sunrise, FL allows us to ensure quality at the highest level. We’re also dedicated to making sure outside resources meet or exceed our high standards.
Get 10% off your first order!
Just sign up for our newsletter for special offers, training tips, and new products alerts. | Learn more about our philosophy and commitment to you.
[Enter email] >
Enjoy the FREE benefits of the Champion Ambition program.
· Save 10% on all orders
· Create a customized program based on your ambition
· Never run out with convenient auto shipments
· Get priority customer service
· No obligation – cancel anytime
> Sign up now!
Our Philosophy Page
Home > Company > Our Philosophy
Who We Are | Our Philosophy
Our Philosophy | We’re here to help you reach your athletic ambitions with a system of products that come out of our longstanding philosophy on healthy and effective sports nutrition.
News & Events
Contact Us | Focus on the Individual
For us, it all starts with you. It’s about using a balanced perspective to develop absolutely great tasting and effective products that align your body and mind, take into account your fitness ambition and level, fit conveniently into your lifestyle, and build on your hard work as you strive to reach your goals.
Get 10% off your first order! | The Right Mix of Healthy Ingredients
Just sign up for our newsletter for special offers, training tips, and new products alerts. | Just as importantly, it’s about providing the right combination of scientifically proven ingredients with a strong nutritional base to help you achieve your specific ambition. You won’t find any artificial flavors, colors, or fillers in our products, and they’re clearly labeled to indicate plant based, dairy free, gluten free, or allergen free.
[Enter email] >
Attention to Your Health
In addition to your ambition, we pay careful attention to your overall wellbeing. Our products offer powerful health boosting ingredients, like antioxidants to protect your body from free radical damage and enzymes, probiotics, and herbal extracts to promote absorption and minimize digestive issues.
Enjoy the FREE benefits of the Champion Ambition program.
· Save 10% on all orders | Commitment to Safety and Quality
· Create a customized program based on your ambition | We have a nearly 30 year history of creating and distributing safe products. Our in-house 135,000 square foot GMP-certified manufacturing facility in Sunrise, FL allows us to ensure quality at the highest level. In addition, we work hard to make sure outside resources meet our high standards.
· Never run out with convenient auto shipments
· Get priority customer service | Explore our products and see how we can help you reach your ambition.
· No obligation – cancel anytime
> Sign up now!
Contact us Page
Home > Company > Contact Us
Who We Are | Contact Us
Our Philosophy | Send us a message by filling in the form below and we will get back to you as soon as possible. All fields are required.
News & Events
Contact Us | Name:
Phone:
Email:
Get 10% off your first order! | Subject:
Just sign up for our newsletter for special offers, training tips, and new products alerts. | Message:
[Enter email] >
[Button: Send]
Enjoy the FREE benefits of the Champion Ambition program. | Champion Nutrition, Inc.
· Save 10% on all orders | 1301 Sawgrass Corporate Parkway
· Create a customized program based on your ambition | Sunrise, FL 33323 USA
· Never run out with convenient auto shipments | Telephone: (954) 233-0320
· Get priority customer service | Fax: (954) 233-3301
· No obligation – cancel anytime | E-mail: info@championnutrition.com
> Sign up now!
U.S. Sales
Customer Service: (800) 225-4831
Fax: (954) 233-3301
E-mail: sales@championnutrition.com
Champion Ambition Program Sign Up Page
Home > Products > Champion Ambition Program
Champion Ambition Program
Sign up for our FREE Champion Ambition program to save 10% on every order. You’ll also be able to create a customized program based on your ambition with recommended products and a convenient auto-shipping feature to help make sure you won’t run out. Plus, you can take advantage of priority service with our dedicated customer satisfaction team.
Sign up now – it’s free and easy with no obligation.
Email:
Password:
Confirm Password:
(Optional) Tell us your ambition, and we can recommend the best products to help reach your goal.
Choose your ambition: [Drop-down: Get Fit and Healthy, Go Farther, Get Stronger, Play Sports Harder]
[Button: Recommend Products]
[Button: Sign Up Now]
Product recommendations open up on clicking Recommended Products button:
Get Fit and Healthy
These Champion products are designed with the nutrition you need to reach your fitness ambitions. Select the ones you’d like to add to your program and check the frequency, then click Save Program. You can sign in and update or cancel it anytime.
[Check Box] Champion Fit (details)
[Frequency Selection TBD]
[Check Box] Champion Energize (details)
[Frequency Selection TBD]
[Check Box] Champion Sustain (details)
[Frequency Selection TBD]
[Check Box] Champion Recharge (details)
[Frequency Selection TBD]
[Check Box] Champion Focus (details)
[Frequency Selection TBD]
[Button: Save Program]
Shopping Cart
Home > Cart
Step 1 |  |  | Step 2 |  | Step 3 |  | [Button: Continue]
Shopping Cart > | Checkout > |  | Receipt >
Please review your order carefully. If you change the quantity, be sure to click Update Cart. Click Continue when you’re done.
Product |  |  | Quantity |  | Unit Price |  | Sub Total
|  |  | Button: Update Cart | Sub Total
Shipping
Tax
TOTAL
[5 empty] | Button: Continue Shopping | Button: Continue
Enjoy the FREE benefits of the Champion Ambition program.
· Save 10% on all orders
· Create a customized program based on your ambition
· Never run out with convenient auto shipments
· Get priority customer service
· No obligation – cancel anytime
> Sign up now!

## SEM Project Plan
Champion Nutrition SEO/SEM Project Plan
Q3 | Task | Task description | Owner | Due Date | Status
June | Kick Off Call | Discovery the digital goals of the website and crete a tactical strategic intitiave to meet those goals as best seen from the search engines point of view. | Entire Team | 2012-06-29 | Completed
July | Banner Display Ad Mock Ups | Begin mock ups banners and spotlights - couple comps of each major size - follow up week before sizzle | Forrest | 2012-07-20 | Scheduled
July | Discovery Questionnaire | Lydia to fill out SEM portion of questionnaire | Lydia | 2012-07-06 | In Progress
July | Discovery Questionnaire | Review Discovery Doc feedback from Client create Client Briefing Doc | Dan |  | Begins with Return of Disco Doc
July | Initial Strategy Build | Create Strategy & Goals based off of Discovery Doc | Dan | 2012-07-31 | To Do
July | Initial Strategy Build | Create Account Campaign Structure i. Structure based off of Client Goals, Site Architecture & Products/Service | Dan | 2012-07-31 | To Do
July | Initial Strategy Build | Build Sample Campaign, Sample Ad Copy & Budgets i. Build 1 Brand Campaign & 1 Non Brand Campaign 1. Create thematic, tightly-knit ad groups (Google KW Tool) 2. Write ad copy that is specific to each ad group, using language from the most relevant page. | Dan | 2012-07-31 | To Do
August | Client Review | Review Account Outline, Strategy/Recommendation Doc, Campaigns, Ad copy suggestions, with Client & Get Approval | Dianna/Dan | 2012-08-30 | To Do
August | Final Campaign Builds | Build Final Campaigns, Ads, Keywords
August | Landing Page Recommendations | Recommend Landing Pages for Campaigns and Call to Actions | Dianna | 2012-08-15 | To Do
August | Create Accounts with Providers | i. Create Google Account (BFO MCC) ii. Create adCenter Account iii. Create Campaign Management Software Account | Dan | TBD | To Do
August | Upload | Upload campaigns into AdWords & AdCenter | Dan | TBD | To Do
August | Billing | Budgets & Billing Setup in Campaign Dashboards | Dan | TBD | To Do
August | Billing | Create Budget/Billing Documents | Dan | TBD | To Do
August | Tracking | Create AdWords Conversion Tracking Tags, Analytics Tracking Tags & Remarketing Tags | Dan | TBD | To Do
August | Tracking | Implement tracking tags | Lydia | TBD | To Do
September | Quality Assurance/Testing | QA/Test - Review each ad for functionality, spelling, URL, tracking | Dan | TBD | To Do
October | Launch/Traffic | SEM Campaign LIVE LAUNCH | Dan | TBD | To Do
October | Launch | Daily check-in and optimization/validations for 1-2 weeks i. Day 1 1. Are we live? 2. Quality Score assessment 3. Ad Preview tool | Dan | TBD | To Do
October | Launch | ii. Day 2 1. Bid strategy/average position assessment 2. Reposition ads to position and goal 3. Set up launch bid strategies | Dan | TBD | To Do
TBD | Ongoing Campaign Maintenance |  | Dan | TBD | To Do
Ongoing | Reporting | Monthly Reporting | Dan | TBD | To Do
Ongoing | Bid/Budget Management | Manage bids/budgets to ensure KPI's in line w/ goals.
Ongoing | Search Query Analysis | Opportunities for negative/additional keywords | Dan | TBD | To Do
Ongoing | Landing Page/Ad Copy Testing | Test LPs & Ad Copy | Dan | TBD | To Do
Ongoing | Quarterly Review | Review Performance Quarterly - areas of opportunity, expansion, etc. | Dan | TBD | To Do