## Sheet1
AGENCY: | CLIENT: | MODULE: | TAG: | PROJECT / TASK / DELIVERABLE / ETC: | DELIVERABLE: | PRIORITY: (1-5 low) | ASSIGNED TO: | NOTES: | DOCUMENTS NEEDED: | BFO DUE: | AGENCY DUE: | CLIENT DUE: | STATUS: | % DONE: | TOTAL EST. HRS: | TIME IT TOOK (OPTIONAL): | HRS PLANNED 8/22-8/28 | HRS PLANNED 8/29-9/4 | HRS PLANNED 9/5-9/11 | HRS PLANNED 9/12-9/18 | HRS PLANNED 9/19-9/25 | HRS PLANNED 9/26-10-2
ZTally | ?? | SEM |  | Search Insight - How people search for the Bahamas. What are they looking for? |  | 4 | Robyn McCleary |  |  | 2011-08-27 |  | 2011-08-28 |  |  | 2
TableXI | ALL | SEM |  | TXI account Recap - Next Steps |  | 2 | Robyn McCleary | It was a REALLY long email…I rewrote it a lot because I was cognisant of the fact that some might take it as if I am coming in and changing everything they have been doing in the past few years. |  | 2011-08-18 |  | 2011-08-18 | Completed | 100% | 1
TableXI | ALL | SEO/SEM |  | Create agenda for Wed meeting w/ Kate |  | 3 | Robyn McCleary | This is my first meeting with Kate - I don't think we're on the same page so I want to come prepared with everything I can in an effort to bring some order to chaos. |  | 2011-08-23 |  | 2011-08-24 |  | 0% | 1.25
BFO | ALL | SEO |  | SEO Project Plan Template Creation |  | 4 | Robyn McCleary |  |  | 2011-08-30 |  | 2011-09-02 |  | 0% | 1
BFO | ALL | SEO |  | Searchlight email |  | 5 | Robyn McCleary |  |  | 2011-08-31 |  | 2011-08-31 |  | 0% | 0.1
BFO | ALL SEO | SEO |  | Review SEO Monthly Report Formats |  | 3 | Robyn McCleary | Ideas for structured reporting |  | 2011-08-23 |  | 2011-08-23 |  | 0% | 2
BFO Direct | Breadkit | SEM |  | Follow up email |  | 2 | Robyn McCleary | Sent Discovery in July - still no word. Also send site questions/updates/reco's - still no word. |  | 2011-08-23 |  | 2011-08-23 | Completed | 100% | 0.25 | 0.15 | 0.25
ZTally | Callaway | SEM |  | Update & Send Callaway Paid Search SOW |  | 1 | Robyn McCleary | Needed it signed & sealed ASAP |  | 2011-08-16 |  | 2011-08-16 | Completed | 100% | 1
ZTally | Callaway | SEM |  | Create Branded campaign ASAP |  | 1 | Robyn McCleary |  |  | 2011-08-18 |  | 2011-08-18 | Completed | 100% | 1.25
ZTally | Callaway | SEM |  | Create Callaway Google AdWords acct |  | 1 | Robyn McCleary |  |  | 2011-08-18 |  | 2011-08-18 | Completed | 40% | 0.25
ZTally | Callaway | SEM |  | Create Callaway gmail account |  | 1 | Robyn McCleary | Tried to use this account to link to Acquisio |  | 2011-08-18 |  | 2011-08-18 | Completed | 100% | 0.1
ZTally | Callaway | SEM |  | Create a structure (campaigns, ad groups, ex. Kw's & copy) for the Callaway campaign |  | 3 | Robyn McCleary |  |  | 2011-08-23 |  | 2011-08-23 | Completed | 100% | 1.25 |  | 1
ZTally | Callaway | SEM |  | Link Callaway AdWords to Acquisio |  | 1 | Robyn McCleary | Can't find the original MCC creator um/pw - huge problem. Need to make magic happen |  | 2011-08-25 |  | 2011-08-25 | In Progress | 25% | 2
ZTally | Callaway | SEM |  | Assign Diacon a task to build out keywords and ad copy for the Callaway account |  | 3 | Robyn McCleary | Dependent on completion of structure |  | 2011-08-26 |  | 2011-08-30 | Completed | 0% | 0.1 |  | 0.1
ZTally | Cooper Tires | SEM |  | New "Official Site" Copy Headlines |  | 2 | Robyn McCleary | Being Reviewed by zTally/Client |  | 2011-07-08 |  |  | Completed
ZTally | Cooper Tires | SEM |  | Competitive Review & Adjustments |  | 2 | Robyn McCleary |  |  | 2011-07-13 |  |  | Completed
ZTally | Cooper Tires | LOCAL SUBMIT |  | Set up Call with Client to Discuss |  | 3 | Robyn McCleary | Robert is setting up a call |  | 2011-07-15 |  |  | Completed
ZTally | Cooper Tires | SEM |  | Fall Rebate Campaign Build |  | 2 | Robyn McCleary |  |  | 2011-08-10 |  | 2011-08-12 | Completed
ZTally | Cooper Tires | SEM |  | Write & Send Cooper Local Media Proposal |  | 1 | Robyn McCleary |  |  | 2011-08-15 |  | 2011-08-15 | Completed | 67% | 1.5
ZTally | Cooper Tires | SEM |  | Write & Send Cooper Local Media SOW |  | 1 | Robyn McCleary | Never delivered a Local Media SOW so I had to rewrite a lot of it. |  | 2011-08-16 |  | 2011-08-15 | Completed | 100% | 2
ZTally | Cooper Tires | SEM |  | Write Labor Day ad copy for the Fall Rebate campaign |  | 1 | Robyn McCleary |  |  | 2011-08-19 |  | 2011-08-19 | Completed | 100% | 0.25
ZTally | Cooper TIres | SEM |  | Create AdCenter Account |  | 3 | Robyn McCleary |  |  | 2011-08-19 |  | 2011-08-19 | Completed
ZTally | Cooper Tires | SEM |  | Upload Fall Rebate campaigns |  | 1 | Robyn McCleary | Waiting on approval of ad copy |  | 2011-08-23 |  | 2011-08-23 | Completed | 100% | 2 | 2 | 2
ZTally | Cooper Tires | SEM |  | Create Local Media accounts in Superpages, CityGrid, and YP.com |  | 1 | Robyn McCleary | May take a lot of time since no one in the office has done this before - not sure what the process is so it's just going to be a test & play type thing until I get it right. |  | 2011-08-24 |  | 2011-08-24 | In Progress | 43% | 3.5
ZTally | Cooper Tires | SEM |  | Local Media account builds |  | 1 | Robyn McCleary |  |  | 2011-08-25 |  | 2011-08-25 | In Progress | 50% | 2
ZTally | Cooper Tires | SEM |  | Upload Local Media accounts |  | 1 | Robyn McCleary | Again - may take a while since I've never done this before. |  | 2011-08-25 |  | 2011-08-25 | Waiting | 0% | 2.5
ZTally | Cooper Tires | SEM |  | Monthy SEM Report - Cooper Tire |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | Monthly AdCopy/Sitelink/Offers |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | Generate and send monthly insights report to client |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | August 2011 Bid Management for Cooper Tire |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | Weekly Review of campaign goals and making recommendations |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | Weekly/Monthly Landing page copy testing |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | Update Monthly Milestone & Notify Rox |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | August 2011 Budget Management for Cooper Tire |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | August 2011 AM/PM Work for Cooper Tire |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-31
ZTally | Cooper Tires | SEM |  | Link Acct to Acquisio |  | 1 | Robyn McCleary | Dependent upon upload of campaigns in AdCenter |  | TBD |  | 2011-08-21 | Waiting | 0% | 1
ZTally | Crystal Coast | SEM |  | adjust spend to $400 min and 11% of media |  | 1 | Robyn McCleary |  |  | 2011-07-01 |  |  | Completed
ZTally | Crystal Coast | SEO |  | Process Pow Wow for SEO |  | 3 | Robyn McCleary | zTally Internal Task |  | 2011-07-01 |  |  | Completed
ZTally | Crystal Coast | SEM |  | Total Account Audit |  | 3 | Robyn McCleary |  |  | 2011-07-15 |  |  | Completed
ZTally | Crystal Coast | SEM |  | Account Rebuild |  | 2 | Robyn McCleary |  |  | 2011-07-15 |  |  | Completed
ZTally | Crystal Coast | SEM |  | Create Crystal Coast Sheet in ZTally Google Doc |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-26 |  |  | To Do |  | 1 |  | 1
ZTally | Crystal Coast | SEM |  | Weekly (Mon/Tuesday/Wed/) or Monthy SEM Report |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-30
ZTally | Crystal Coast | SEM |  | Send Discovery/Survey to Client |  |  | Robyn McCleary | Reassigned per Josh |  | 2011-08-30